## Team
| Name | Role | Comments
Scrum Team | Me | Agile Delivery Lead
| Patty | Product Owner | Late for stand ups. Needs to engage the developers with refinements so that they know whats coming up, and that items are ready. Seems to interrupt the developers a lot while they are working. Didn't add details to the new PBIs quickly, but need to raise any blockers.
| Dave | Lead Developer | Took on Debs' work for Prish
| Darren | Developer | Agreed to drop current work and context switch. Complered 3 items on the sprint in isolation, and started, but didn't finish another item
| Darcy | Developer | Asked to work late by Cathy
| Dianne | Developer | Wasn't mentioned much, what did she do?
| Debs | Developer | Asked to work late by Cathy. Worked on Prish's item but context switched.
| Tim | Tester | Works late to test PBI 58712. Struggled with the test environment. Had a holiday
| Tina | Tester | Skipped one standup. Ran manual regression
| Cathy | CEO | Asked PO for status, asked team to work late
Stakeholders | Pam | Product Manager | Was asked by Patty for details of a PBI
| Olga | Ops Team | Not involved
| Oli | Ops Team | Not involved
| Sara | Sales | Sometime didn't turn up to the stand-up, sometimes interrupted. Escalated issue to Cathy
| Prish | Project Manager | Didn't attend stand-ups, and wasn't aware of scope changing. Interrupts the stand up. Talks to the team rather than through the PO
| Q | Head of Quality

## Events
Event | Comments
Sprint | Items rolled from the last sprint. Some PBIs were completed. but 1 PBI was not completed, and one unstarted PBI rolled to the next sprint. Sprint scope was compromised by adding a PBI that was not ready.
Planning | Planning starts a bit late, as the next sprint starts straightaway after the last one. The team should have refined the PBIs and should know what’s coming up, it shouldn’t be a surprise. The team should negotiate what to include in a sprint, and be comfortable to only include items that ready, and that they think they can complete.
Daily Scrum | Patty late. Some people have sporadic attendance. Cancelled once. Its OK to have lots of people at the stand up, but only the scrum team can participate, unless the team want to actively ask questions. Others should observe. Scrum team members should set daily targets and discuss how they are progressing towards the sprint goal, and what to do next.
Refinements | The team could have a “Definition of Ready”, at least they shouldn’t accept items that are poorly defined. They need to have a good idea of size and complexity to understand whether they can complete the items
Review | This event didn't really take place. The team did a demo, but that’s only an element of a Sprint Review. Ideally the team would talk about: + What they planned + What did they complete, what didn't they complete + What problems did they have and how did they overcome them + Demo + Whats coming next
Retro

## Artifacts
Artifact | Comments
Increment | Didn't appear to create one as an output of the sprint
Product Backlog
Sprint Backlog